**Bartlett Cocke Const.** **Killeen East Ward/West Ward Consolidation**

**Monthly Progress Report – April 2020**

****

**Sections 3:** Exterior CFMF framing in progress with gup. Sheathing and fluid-applied waterproofing to follow

**Section 1 Roof:** PVC roofing substantially complete with rooftop units to follow

**Section 5 Ext:** Stone masonry in progress with aluminum framed windows and metal wall panel z-furring to follow

**Site:** Sanitary water line backfill in progress

****

# This Month’s Major Activities:

* Section 1: Roof: PVC Roofing
* Section 3: Exterior CFMF Walls
* Sections 4 & 5 Ext: Window Flashing
* Sections 4 & 5 Ext: Fluid-Applied Waterproofing
* Sections 4 & 5 Ext: Stone Masonry

# Next Month’s Major Activities:

* Section 3 Ext: Fluid-Applied Waterproofing
* Sections 4 & 5 L1: In-Wall Blocking
* Sections 4 & 5 Ext: Window Flashing
* Sections 4 & 5 Ext: Stone Masonry
* Section 5 Ext: Aluminum-Framed Windows

Design Percent Complete – 100% Construction Percent Complete – 37.57%