**Bartlett Cocke Const.** **Killeen East Ward/West Ward Consolidation**

**Monthly Progress Report – May 2020**



**Sections 4 L11:** 1 side gyp board in progress with sound batt. Insulation to follow

**Section 3:** Roof System above the cafeteria in progress.

**Section 8 & 9 L3:** CFMF and mechanical duct risers in progress with gyp board top out to follow

**Sections 4 & 5 Ext.:** Aluminum frames & glazing complete with metal wall shingle system for follow water testing.

****

# This Month’s Major Activities:

* Sect. 2: Fluid Applied Waterproofing at CMU
* Sect. 2: Spray fireproofing at beams and deck
* Sect. 2 & 3: KEE Roofing System
* Sect. 4 & 5: Alum. Frames, glazing and masonry
* Sect. 4 & 5 L1: Gyp board & sound batt. Insulation
* Sect. 6 & 7 L2: Pressure Testing at HVAC Duct
* Sect. 8 & 9 L3: CFMF and MEP rough-in
* Electrical Rooms: Tape, float, and paint

# Next Month’s Major Activities:

* Sect. 2: Masonry and flashing at brick lug
* Sect. 3: 80mil KEE Roofing System
* Sect. 4 L1: Gyp board and insulation
* Sect. 6 & 7 L2: In-wall blocking and support
* Sect 6 & 7 L2: In-wall rough-in deficiency punch
* Sect. 8 & 9 L3: CFMF and MEP rough-in
* Transformer and primary wire pull
* Envelope and window testing

Design Percent Complete – 100% Construction Percent Complete – 41.96%