**Bartlett Cocke Const.** **Killeen East Ward/West Ward Consolidation**

**Monthly Progress Report – July 2020**



**Sect. 1:**  One side gyp board is complete

**Sect.3 & 5 EXT:** Glazing for curtain walls is complete

**Sect. 4 & 5 Corridor:** Firs coat of finish paint on fur down complete

**Site:**  Form board and rebar for south side parking lot in progress with concrete paving to follow

****

# This Month’s Major Activities:

* **Sect. 1:** Plumbing hanger rough in
* **Sect. 1 & 3:** Start glass install for curtain walls
* **Sect. 4:** Start hanging ceiling grid & light fixtures
* **Sect. 6 & 7 L2:** Start gyp board at fur downs
* **Sect. 8 & 9 L3:** Complete overhead duct
* **Site:** Complete rough grade for conduit
* **Site:** Start for boards for parking lot concrete

# Next Month’s Major Activities:

* **Sect. 1:** Plumbing hanger rough in
* **Sect. 1 & 3:** Glass for curtain walls complete
* **Sect. 4 & 5:** Low-volt race ways supports in progress
* **Sect. 4 & 5 EXT:** Complete masonry veneer
* **Sect. 6 & 7:** Start firs coat paint
* **Sect 8:** Finish mechanical in wall
* **Site:** Complete form boards and tying rebar
* **Site:**  Concrete paving for parking lot

**Site:**

Design Percent Complete – 100% Construction Percent Complete – 43.2%