## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - August 2020
SEC 1: Corridor framing and insulation is complete
SEC 2: Activity room fur down for folding panel partition is complete
SEC 3: Cafeteria gyp board is in progress
Sec 2 EXT: Activity room masonry is in progress
This Month's Major Activities:
SEC 1: Gyp board in classrooms are complete
Sec 1 & 2: MEP overhead is in progress
SEC 3: Freezer and cooler install in progress
SEC 5: Library fur downs are in progress
SEC 6 & 7: Casework install in progress
SEC 8: Gyp board two side in progress
SEC 9: Tape and float in progress
SITE: Installation of parking lot light poles
Next Month's Major Activities:
SEC 1: Complete duct install
SEC 2: Complete plumbing to out
SEC 3: Complete gyp board at stage area
SEC 4 & 5: Install casework counter tops
SEC 5: Start tile in stair wells
SEC 6 & 7: Texture hard lid ceilings
SEC 8: Complete two side gyp board
SITE: Install parking lot light poles
Design Percent Complete - 100%
Construction Percent Complete - 53.2%