## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - Sept. 2020
SEC 1: Texture complete production paint in progress
SEC 3: HVAC duct complete framing for ceiling clouds in progress
SEC 5: Classroom flooring & casework installation in progress
SEC 6 & 7: Corridor tile in progress
This Month's Major Activities:
  SEC 1: Tape and float in progress
  SEC 1 EXT: Masonry in progress
  SEC 3: Start tile in kitchen
  SEC 3: Grease duct complete & fire wrap to follow
  SEC 4 & 5: Corridor stair well tile in progress
  SEC 5: Classroom LVT installation in progress
  SEC 8 & 9: Complete ceiling grids
  Site: Start grading for Fencecrete
Next Month's Major Activities:
  SEC 1 EXT: Masonry in progress
  SEC 2 EXT: Masonry at PE room in progress
  SEC 2: Start duct install in PE room
  SEC 3: Start tape and float at stage
  SEC 3: Fire wrap grease duct
  SEC 4 & 5: Classroom flooring in progress
  SEC 8 & 9 EXT: Metal shingles in progress
  Site: Grading for Fencecrete installation
Design Percent Complete - 100%
Construction Percent Complete - 58.5%