## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - Oct. 2020
SEC 5: Linear wood ceiling in progress
SEC 8 & 9: Ceiling grip is complete
SOUTH EXT: Gyp. Board at columns complete
WEST EXT: Cisterns are in progress
This Month's Major Activities:
  SEC 1: Casework in progress
  SEC 1: Duct in progress
  SEC 2 EXT: Activity Room masonry in progress
  SEC 3: Kitchen floor tile in progress
  SEC 5: Ceramic tile to star at stairwell
  SEC 8&9: Ceiling grid is complete
  Site: Canopy install is in progress
  Site: Install retaining wall & Fencecrete
Next Month's Major Activities:
  SEC 1: Start elevator install
  SEC 2: install lighting in Activity Room
  SEC 3: Start quarry will tile at kitchen
  SEC 5: Start sheet vinyl in restrooms
  SEC 8&9: Install HVAC flex and grills
  Roof: Gas pipe installation in progress
  Site: Canopy install in progress
  Site: Continue install of retaining wall and Fencecrete
Design Percent Complete - 100%
Construction Percent Complete - 68.4%