## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - August 2020
SEC 3: Kitchen equipment install in progress
SEC 5: Rubber base install in progress
SITE: Retaining wall in progress
OVERALL BUILDING
This Month's Major Activities:
  SEC 2: Elevator install in progress
  SEC 3 EXT: Masonry at canopy columns in progress
  SEC 4 & 5: plumbing fixtures at group restrooms
  SEC 6 & 7: Install tack boards
  North EXT: Install phenolic at main canopy
  SEC 8 & 9 EXT: East side masonry in progress
  SEC 9: Grout tile at corridors
  Site: Install retaining wall in progress
Next Month's Major Activities:
  SEC 3 EXT: Continue masonry at canopy
  SEC 4 & 5: Continue setting tile in corridor
  SEC 2: Complete elevator install
  SEC 5: Continue with rubber base install
  SEC 6 & 7: Installation of ceiling tiles
  SEC 9 EXT: Continue north side masonry
  SITE: East side grading for bus loop
  SITE: Continue installation on retaining wall
Design Percent Complete - 100%
Construction Percent Complete - 73.2%