## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - Dec. 2020
SEC 3: Lights and ceiling grid at stage is complete
SEC 5: Lights and aluminum framed store front is complete
SEC 8: Flooring in corridors in progress
Site: December 2020
This Month's Major Activities:
SEC 2: Elevator install is complete
SEC 3: Ceiling grid and ceiling tiles are in progress
SEC 5: Library light fixtures are complete
SEC 5 EXT: Masonry at canopy columns is in progress
SEC 6 & 7: Install Plumbing fixtures at group restrooms
SEC 8 & 9 EXT: East side masonry is in progress
SEC 8 & 9: Rubber base in corridors is in progress
Site: East grading for bus loop is in progress
Next Month's Major Activities:
SEC 1: Data is being ran for added IDF room
SEC 4: Terrazzo at west stairs case is in progress
SEC 5: Lights at intersections are in progress
SEC 5 EXT: Masonry at canopy columns is in progress
SEC 6 & 7: Install Plumbing fixtures at group restrooms
SEC 8 & 9: Rubber base in corridors is in progress
Site: East and west CMU block is in progress at cisterns
Site: East grading for bus loop is in progress
Design Percent Complete - 100%
Construction Percent Complete - 77.9%