## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - February 2021
SEC 3: Cafeteria Flooring is complete
SEC 3: Stage tile and Cafeteria flooring is in progress
East EXT: Canopy is in progress
SITE: Fencing is in progress
This Month's Major Activities:
SEC 2: Install Graphic wall panels at activities room
SEC 3: Cafeteria flooring is Complete
SEC 3: Stage tile and flooring is complete
SEC 3: Elevator is in progress
West Stairwell: Sealing terrazzo stairs
North EXT: Flatwork is in progress
North EXT: Install flag pole Complete
Site: Irrigation is in progress
Next Month's Major Activities:
SEC 2: Install Graphic wall panels at activities room
SEC 3: Stage phenolic is in progress
SEC 3: Install flooring in elevator
East EXT: Handrails in progress
South EXT: Canopy lighting is in progress
Site: Fencing is in progress
Site: Tree install is in progress
Site: Flat work in progress
Design Percent Complete - 100%
Construction Percent Complete - 81.7%