## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - March 2021
Main Entry: SOD & fencing substantially complete and ready for landscape & irrigation final.
Activities: Plastic Laminate graphics wall complete.
Library: Lighting Controls complete & ready for KISD furniture move-in.
Site: Playgrounds & Playcourt complete.
This Month's Major Activities:
INT. BUILDING: A/O Punch work-off & final clean
KITCHEN: Kitchen Punch
EXT. BUILDING: Bartlett Cocke work off punch list
SITE: Sod, fencing & striping
OVERALL BUILDING: Temporary CO
Next Month's Major Activities:
INT. BUILDING: MEP & Technology Punch Walk
KITCHEN: Health Inspection
OVERALL BUILDING: Killeen ISD furniture move-in & CO
EXT. BUILDING: A/O Punch Walk & Work-off
SITE: Landscaping & Irrigation Punch & Site Final
Design Percent Complete - 100%
Construction Percent Complete - 87.7%