## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - August 2020
Main Entry
2nd Floor Administration: KISD office furniture move in complete.
Kitchen
Library: KISD furniture move-in in progress
This Month's Major Activities:
INT. BUILDING: KISD classroom furniture move in
INT. BUILDING: Work on Architect/Owner punch list
EXT. BUILDING: Work on Architect/Owner punch list
SITE: Work on Landscape & Civil Final punch list
OVERALL BUILDING: Certificate of Occupancy issued 4/22/2021
Next Month's Major Activities:
INT. BUILDING: Technology Punch Walk
INT. BUILDING: Continue KISD classroom furniture move in
INT. BUILDING: Continue Architect/Owner punch list
EXT. BUILDING: Continue Architect/Owner punch Iist
SITE: Work on Landscape & Civil Final punch list
Design Percent Complete - 100%
Construction Percent Complete - 88.2%