## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - May 2021
Overall Site
Campus Branding
Furniture Move-in at Administration Area
Exterior: Grounds maintenance has begun
This Month's Major Activities:
  Exterior: Final punch list items being completed.
  Interior: Final punch list items being completed.
  Interior: Offices and classrooms being outfitted with furniture.
  Exterior: Grounds maintenance has begun.
Next Month's Major Activities:
  Interior: Receive warehouse deliveries.
  Interior: Receive teacher's belonging from West Ward.
  Interior: Installation of small appliances.
  Interior: Administration Staff moves in.
  Interior: Begin Reception area enhancements.
  Exterior: Begin additional fencing at playground and cisterns.
Design Percent Complete - 100%
Construction Percent Complete - 88.5%