## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - June 2021
Construction is complete and the campus is open
Killeen Elementary School Graphics & Branding
Enhancements of the Reception Area
Installation of fencing around the cisterns
This Month's Major Activities:
  Exterior: Final punch list items being completed.
  Interior: Final punch list items being completed.
  Enhancements of the reception area complete
  Safety fencing around cisterns is installed.
Next Month's Major Activities:
  Install corner guards at the stage
  Install rear and side stage curtains
  Install translucent lenses at corridors
  Curb and ramp modifications at Stone Ave
  Install campus graphics and branding
  Install gate hardware at playground
Design Percent Complete - 100%
Construction Percent Complete - 100%