## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - July 2021
Construction is complete and the campus is open
Killeen Elementary School Graphics & Branding
Enhancements of the Reception Area
Library
This Month's Major Activities:
  Interior, Exterior & Site: Responding to warranty calls.
  Received approval from COK for drainage modification to Patton Dr. & Stone Ave
Next Month's Major Activities:
  Dedication ceremony
  Start of school
  Installation of column graphics (branding)
  Interior, Exterior & Site: Responding to warranty calls
Design Percent Complete - 100%
Construction Percent Complete - 100%