## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - August 2021
Construction is complete and the campus is open
Installation of School Graphics & Branding
Activity Room
Playground
This Month's Major Activities:
  Interior, Exterior & Site: Responding to warranty calls.
  Delayed modification to Patton Dr. & Stone Ave until Christmas Break
Next Month's Major Activities:
  Continue installation of column graphics in Library (branding)
  Interior, Exterior & Site: Responding to warranty calls
Design Percent Complete - 100%
Construction Percent Complete - 100%