## Sheet1
Bartlett Cocke Construction East Ward/West Ward Consolidation
Monthly Progress Report - September 2021
Construction is complete and the campus is open
Installation of Library Cloumn Wraps
Activity Room
Installation of Graphics & Branding
This Month's Major Activities:
  Interior, Exterior & Site: Responding to warranty calls.
  Delayed modification to Patton Dr. & Stone Ave until Christmas Break
Next Month's Major Activities:
  Interior, Exterior & Site: Responding to warranty calls
Design Percent Complete - 100%
Construction Percent Complete - 100%